Project Management

Playbook

DRAFT v 1.0

# Table of Contents

1. Introduction	2

2. Intended Audience	2

3. Forsys Project Execution Methodology	2

4. Planning Phase	2

5. Define Phase	3

5.1. Before the Discovery Session	3

5.2. In the Discovery Session	3

5.3. Post the Discovery Session	4

5.4. Documentation	4

5.5. Review Sessions	4

5.6. Common scenarios in Discovery Sessions	5

5.7. Useful Tools and Techniques for conducting discovery sessions	5

6. Design Phase	5

6.1. Before the Design Sessions	5

6.2. In Design Sessions	6

6.3. Post Design Sessions	6

6.4. Documentation	6

6.5. Review Sessions	7

7. Build Phase	7

7.1. Build Phase Preparation	7

7.2. In Build Phase	7

8. QA Phase	8

8.1. QA Phase Preparation	8

8.2. In QA Phase	8

9. UAT Phase	8

9.1. UAT Phase Preparation	8

9.2. In UAT Phase	8

10. Go Live	9

10.1. Go Live Preparation	9

10.2. During Go-Live	9

10.3. Post Go-Live	9

11. Training, Skills and Additional Content for a Project Manager	9

## Introduction

This playbook is created to act as a standard process guide for the execution of the project manager (PM) job function as part of the deployments managed by Forsys. This will list all the processes, tools, templates, standards and standardized content available to perform the job function.

## Intended Audience

All new PMs who are a part of the Delivery  group need to go through the playbook. The document will be owned and maintained by the Delivery group and should be updated once a year thereby making it mandatory for all the below users to go through this document once a year.

- Technical Project Managers

- Delivery Managers

- Delivery Directors

- Engagement Manager

- Engagement Director

## Forsys Project Execution Methodology

Link to Forsys Project Execution Methodology

## Planning Phase

  - Review the pre-sales stage content available in the Project documentation folder. Below content needs to be reviewed

- Completed Discovery Questionnaire

- Recordings of the conversations with Customer

- Proposal Deck

- SOW

- Price sheet

- Resource estimates

  - Create Kickoff Deck

Kick Off Deck

  - Structure the discovery content based on the process areas and sub-process areas available for the Industry/domain/solution. Below are the links to the standardized process areas and requirements

Link to standard documentation/templates

  - Make a copy of the OOB user stories into the Project documentation and Identify the OOB user stories vs Additional user stories specific to the customer.

  - Prepare detailed Project Plan. Here is the link to Project Plan

  - Prepare the plan for discovery of each process area in coordination with Project Manager / SA / TA that can be reviewed with the customer. The completed plan should have the agenda, dates, sessions,  stakeholders availability and customer alignment

  - Prepare the content for each session to drive the discussions. The internal review of the content should be done with SA/PM everyday before the next day's call.

  - Initiate development of overall project plan

  - Create/Initiate standard documents for the project

    - Initiate Burn Down Report

    - RAID Log

    - Confirm team structure and team members and formally request resources

    - Establish project control, and reporting procedure

    - Initiate introduction to customer with PM-to-PM call to review methodology and timeline

    - Create Weekly Status Report. Use the =Weekly Status Report Template

Link to standard documentation/templates

  - Share the standard templates and documentation that we would need from the customer. For Eg: Agreement Templates , Product/Pricing Templates etc..

## Define Phase

### Before the Discovery Session

    - Share the Agenda for the upcoming two weeks for the Define Phase sessions.

    - Share the content to be reviewed with stakeholders at least 2 days in advance.

### In the Discovery Session

    - Set the context before every session. The context should give details of

- Recap of the previous session if needed

  - Including reviewing any open questions or confirm clarity that may have been given during or after the previous session

- key roles (key participants, scribe..)

- Agenda of the session

- Expected outcomes of the session

- Review list of action items and deliverables( with target dates) from session

    - Always start with the overall process diagram and highlight the process area / areas to be covered as part of the session.

    - Review the Current State End to End Process flow as part of Business process review  in terms of

- Actors

- Business Process

- Manual Touch Points

- Pain Points

- Integrations

- Desired output or conclusion

Link to standard documentation/templates

    - Refine each requirement with the below process details

- Actors

- Requirement Detail/ User Story

- Acceptance Criteria

- Dependencies

- Assumptions

- Open Items

- Priority

Link to standard documentation/templates

    - Always block the last 5 mins of the session to

- Brief outline of the discussion completed

- Review the Key decisions, actions, owners and the deadlines.

- Additional sessions if any needed.

    - Deliverables:

    - Deliverables:

      - Project Plan: The Project Plan baseline identifies all phases, activities, tasks, deliverables, assigned resources, milestones, and target completion dates.

      - Contact List: List of team members with contact information

      - Project Control and Reporting Procedures: This deliverable specifies the project management controls and reporting mechanisms to be used during the duration of the project. Includes processes for status reporting, change control, issue tracking and the role of the steering committee.

      - Installation Plan: Confirmed dates for installation of software in different environments based on hardware/software availability.

      - Kick-Off Presentation: PowerPoint presentation for the kick-off. This will provide information about the project scope, milestone and team composition and will be presented to all key stakeholders.

      - Create a resource spreadsheet and input resources required into system for allocation

      - Functional Requirements Document (BRD): This deliverable contains detailed descriptions of functional requirements.

      - Process Flows: This deliverable includes a series of models (process model, workflow models, etc.) which outline the client’s business processes in detail as well as how these processes will be mapped to the software

      - High-Level Solution Architecture: This document captures the overall solution architecture and the integration components to be implemented as part of the solution. It also captures the data flow and frequencies of the flow of the integrated systems.

      - Gap Analysis: List of the system limitations and proposed work arounds

      - Comparison and analysis of SOW vs BRD to identify any scope changes with potential project plan changes

### Post the Discovery Session

    - Share the content reviewed in the meeting with the meeting notes along with the session recording

    - Share the MOM captured as part of the session with the notes,  decisions, actions.

Link to standard documentation/templates

MOM Template

    - Update the Project RAID log

Link to standard documentation/templates

RAID Log

### Documentation

    - At the end of the discovery week in the internal review and prep sessions document the below. This should be an activity to be closed every week.

- Business Requirements Document (BRD)

- Documents Required from the customer

- As-Is and To-Be Business Process Flows

- Refined Requirements ( Updated in JIRA or Project tool as needed)

- Review and compare Refined Requirements to the SOW to identify differences

Link to standard documentation/templates

    - Update the internal project reference documentation that captures

- Session Recording links

- MOM for each session

- Update the Project RAID log

Link to standard documentation/templates

    - Modify & Communicate the following week’s sessions , agenda and content based on the current week’s discussions.

    - Review the documentation from the customer ( From Step 4.6) and highlight any missing data or additional information required.

### Review Sessions

    - At the end of every week, review the completed documentation with Solution Architect / Project Manager

    - At 100% (phases based on project size) completion, review the completed documentation with Solutions COE and complete the Define Gate check. Refer the gate check template

    - Share & Review with the customer after the Solutions COE review is completed and get the Sign off

    - Include the extended teams (QA, Dev) as part of the End of the week Internal Reviews  for them to be aware of the functionality

Link to the Checklist to be completed

### Common scenarios in Discovery Sessions

- Off Track Discussions

- Conflicting Requirements

- Missing Contexts

- Not reading the room

- No Business Owner

- Out of scope requirements

- Stakeholders Missing

- Too much Focus on Exception Cases

- Non-standard use cases

## Design Phase

### Before the Design Sessions

    - Work with Solution Architect and Technical Lead to identify the design phase plan, sessions and agenda

Link to the sample design plan

    - Communicate the Weekly Design Phase sessions and agenda to the customer stakeholders.

    - Schedule the Internal design & review sessions as agreed with the key stakeholders before the customer sessions

    - Maintain the traceability of the requirements in the design documentation.

Link to sample design document

https://docs.google.com/spreadsheets/d/1Gg4W2tmwaWqFQHpTqFxk3EVdWVuLKFrz/edit?usp=sharing&ouid=101935984536383661546&rtpof=true&sd=true

    - Provide the design sessions documentation with respect to the requirements being covered at least 2 days ahead of the session

Link to sample design document

### In Design Sessions

    - Set the context of the discussion

- Recap of the previous session if needed

- Key roles (key participants, scribe..)

- Agenda of the session ( Process area / Requirements)

- Expected outcomes of the session

    - Add the business context or additional details to the discussion wherever needed.

    - Author the MOM based on the design discussions

    - Always track the time and block the last 5 mins to review

- Brief outline of the discussion completed

- Review the Key decisions, actions, owners and the deadlines.

- Additional sessions if any needed.

### Post Design Sessions

    - Share the content reviewed in the meeting with the meeting notes along with the session recording

    - Share the MOM captured as part of the session with the notes,  decisions, actions.

Link to standard documentation/templates

MOM Template

    - Update the Project RAID log

Link to standard documentation/templates

RAID Log

### Documentation

    - At the end of the design week in the internal review and prep sessions document the below. This should be an activity to be closed every week.

- Business Requirements Traceability to Design

- Updating the Requirement details and status in JIRA or Project tool as needed

Link to standard documentation/templates

SDD Template

    - Update the internal project reference documentation that captures

- Session Recording links

- MOM for each session

- Update the Project RAID log

Link to standard documentation/templates

    - Modify and communicate the following week’s sessions , agenda and content based on the current week’s discussions. This should refine the documents created in steps 6.1.1 and 6.1.5

    - Review the documentation from the customer ( From Step 4.6) and highlight any missing data or additional information required.

### Review Sessions

    - At the end of every week, participate in the review of  the completed design documentation with Solution Architect / Project Manager and Internal Teams

    - At 100% completion (phases based on project size),review the completed documentation with Solutions COE and complete the Define Gate check. Refer the gate check template

    - Share & Review the design document with the customer after the Solutions COE review is completed and get the sign off

    - Include the extended teams (QA, Dev) as part of the End of the week Internal Reviews  for them to be aware of the functionality

    - Participate in Internal Review and provide Sign off on the Test scenario and Test case documentation.

  - Deliverables

    - Foundational/Solution Design SDD): This document captures all the configuration changes that can be made using standard application functionality that are required to implement the requirements covered in Functional Requirement document.

    - Integration Design: This document captures the end to end integration design along with data flow required to complete the integration between CPQ/CLM and other systems.

    - Data Migration Design: This document captures the overall data migration design including strategy around extract and loading of master data, reference data and contract data.

    - Custom Component Design: This document captures the design of all custom components that are required to be built as per the requirement and gap analysis document.

    - Test Plan: Test Plans are developed which describe the application Test Environment, the Functional Test Plans and the System & Integration Test Plans.

    - Training Strategy and Plan: As part of Design, Training and Documentation Outlines and Configurations are developed which identify the training curriculum, course modules and documentation components to support the new system.

    - Communication Plan: This document sets clear guidelines for how information will be shared to Stakeholders, as well as who’s responsible for and needs to be looped in on each project communication.

    - Updated Project Plan: Once the design is complete and all requirements are known the Development Plan is updated with more specific tasks and actual date of completion of the tasks.

Link to the Checklist to be completed

High Level Test Scenarios

## Build Phase

### In Build Phase

Upon approval of Design deliverables (SDD sign off), development of the new application can commence. A team of Forsys functional analysts perform this work. The specifications and working prototypes developed during Analyze and Design are used to configure a client-specific application.

During the build phase we will continue to validate and refine design components that can be modified using standard application functionality and those that do not have major impact on the development activity.

    - Sprint-0 Activities -

- 7.1.1.1. Build Environment Access to the entire Build Team

- 7.1.1.2. PM should walkthrough the entire BUILD Process to the team and focus on the compliance of the Quality checks.

- 7.1.1.3. Build Sprints Communication Cadence - Sprint Planning , Daily Scrum/Standup Call , Sprint Review , Backlog Refinement Meeting , Sprint Retrospective ,  any other required calls.

Note : All the required meetings (One Time or Recurring - Should plan in advance and well informed to the customer)

- 7.1.1.4. Ensure the User Stories are prioritized in the Backlog and have the complete details for the estimation (Acceptance Criteria and Solution Design)

- 7.1.1.5. User Stories in JIRA should be properly linked with the respective EPICS.

- 7.1.1.6. PM should conduct the sessions : (BA & SA) with the Build Team. Expectation is to guide & clarify all the doubts for the prioritized user stories acceptance criteria and solution design.

- 7.1.1.7. Development Team plan and estimate for the Sprint-1. Team can start the breakdown of the User Stories in the sub tasks for the simplification of the required tasks to complete and estimate it.

- 7.1.1.8. Sprint Plan for the Sprint-1  should be created with the clear list of the User Stories to deliver. Development Team will be responsible for creating the Sprint plan after discussing the Priorities with the Business Team. Sprint Plan should be created in JIRA or any other tool using in the Project.

- 7.1.1.9. Customer Tools, Standards and Guidelines trainings are the part of Sprint-0

- 7.1.1.10.Customer CI/CD Pipleline and Processes need to aligned.

- 7.1.1.11.PM should ensure for the update of the Technical Design Document. Technical Lead is responsible for working on the TDD with the development team.

TDD Reference Document -

- 7.1.1.12 - All data required for testing and subsequent migration is shared by the customer teams

    - Mentioned above steps in the Sprint-0 will be repeated for all the Build Sprints.

    - PM should send the committed Sprint Plan to all the stakeholders via EMAIL.

    - Following are the sub tasks which are required for maintaining the quality of the user story

- Unit testing - Expecting to add the Unit Test Results. Creating the document with the evidence and add the Unit Test Results.

Follow the Unit Testing Guidelines

https://docs.google.com/spreadsheets/d/1yXVi8k2BtYXLIFSO_ItIabigvgHEPuoQ/edit?usp=sharing&ouid=101935984536383661546&rtpof=true&sd=true

- Code Review - This is the necessary step before the deployment to the higher org. Code review should be done by peer or lead and the proper evidence of the code review should be maintained.

Only on the basis of the closure of this task will move for the deployment.

- Configuration Log Update - Maintain the file for the configuration log to update for every user story.

Configuration Log - FILE

NOTE : If any user story doesn’t required the configuration or customization these stories will also needs to add in the LOG with clearly mentioned of no configuration and customization required.

    - Business Team should provide internal sign off on the complete build based on internal demo and requirements and complete the build gate check. Refer the Gate check Document

    - All queries of the Build Team will be timely resolved by the Business & Solutions Team.

PM should update the RAID LOG.

    - PM should track all the dependencies in terms of clarification. Very clearly segregate the Dependencies owner in the tracker with the due dates.

Dependency tracker : https://docs.google.com/spreadsheets/d/199GLTQ9TM8ZCGZaGlF-wIXzwbL_bomcOtuTfLt-jnPM/edit?usp=sharing

    - On the basis of the scheduled Sprint Demo with the entire customer team. Business Analyst along with the Solution and Build Team will give the demo.

    - PM to ensure the MOM should be created and addressing all the feedbacks from the customer and send it across to all the members.

Note : Every Demo should be recorded and must send along with the MOM.

    - PM should send the Sprint Closure Report to all the Stakeholders

- Sprint Closure Report Document Reference

https://docs.google.com/spreadsheets/d/1JRcGdffDuhFScljF4RC0qFI78FoB-TXv8InXEIWA6SA/edit?usp=sharing

    - PM should work with the Team and prepare the SIT Cutover Plan. This plan should be ready and discussed with the Customer (Business , DevOps , Technical and PMO) Team.

Link to the Checklist to be completed

https://docs.google.com/spreadsheets/d/1pwft6r0YzIIEUaT8KfKKMguYpQpgp1e7/edit?usp=sharing&ouid=101935984536383661546&rtpof=true&sd=true

Deliverables

Configured Application and Constructed Interfaces: Forsys will leverage Windows technology, as well as other sophisticated development tools to rapidly develop and deploy the application in the client’s environment. Depending on the size and complexity of the application, Forsys suggests a “divide and conquer” development approach where application functionality is partitioned across application teams and/or ordered in an incremental development schedule. This iterative approach demonstrates early functionality to the client, achieves their buy-in, and demonstrates early success. Additional features and functionality are introduced in subsequent iterations. Construction includes unit testing what is built. For unit test, the project team will: execute the unit test plan, resolve any bugs/issues, and re-test areas where bug fixes have occurred.

Data Load Files and Analysis: Forsys will prepare a formatted data extract file for Legacy contracts and Master data for import into the configured QTC solution. Additionally, Forsys will analyze this data for relevant tangible examples, e.g., evergreen contracts with auto renewal provisions; upcoming expiration dates that are scheduled to occur during and within the first week of project go-live; deviations from standard language that support the business case for the client’s QTC Program.

Update Documentation: The project team will: inform other developers and related team members of any changes that were made to the original design, update the Design and Analyze documentation based on the construction, notify the testers of any changes that were made, and update the Functional Test Plan based on the

## QA Phase

### QA Phase Preparation

    - Participate in the Test Case Review sessions with the customer.

    - Resolve any open questions that the QA team might have along with the Solution Architect

### In QA Phase

The test allows all parties to confirm that the system meets requirements and design. Upon completion of Build which includes unit testing, Forsys will coordinate with the client to complete the System Integration Test as required based on the design. All integration related issues will be cleared before the system is ready for User Acceptance Test (UAT).

UAT will be performed by client stakeholders with Forsys providing support to manage the issue resolution process.

Typically, Test is an iterative process to identify and resolve issues until the system is ready for launch.

    - Participate in the Defect Triaging calls

    - Coordinate with customer/solution architect and other stakeholders to provide feedback on the open defects wherever the clarification is required.

    - Conduct ad-hoc testing for the end to end flow based on the UAT scenarios and report any issues identified to the project team.

    - Deployment Tracker for the SIT Deployment

Link to the Checklist to be completed

https://docs.google.com/spreadsheets/d/1q-MtmyFXa1isSzC51wiusqfpy7iKFAfZe3PxDtXhyK4/edit?usp=sharing

    - UAT Cutover Plan

Link to the Checklist to be completed

https://docs.google.com/spreadsheets/d/1pwft6r0YzIIEUaT8KfKKMguYpQpgp1e7/edit?usp=sharing&ouid=101935984536383661546&rtpof=true&sd=true

## UAT Phase

### UAT Phase Preparation

    - Review the UAT Test Cases from the customer.

    - Identify and coordinate with the QA team on any data setups required for the UAT execution.

    - Review the UAT demo scenarios and documentation prepared by the QA team to be provided to the customer.

### In UAT Phase

    - Participate in the UAT sessions along with the QA lead.

    - Provide clarification on any business scenario or functionality related questions raised as part of the UAT sessions.

    - Participate in the Defect Triaging calls of the customer.

    - Execute the final testing on UAT defects before assigning the defects back to the customer.

    - Conduct UAT demos in coordination with the QA team as required.

    - Deployment Tracker for the UAT Deployment

Link to the Checklist to be completed

https://docs.google.com/spreadsheets/d/1q-MtmyFXa1isSzC51wiusqfpy7iKFAfZe3PxDtXhyK4/edit?usp=sharing

    - Production Cutover Plan

Link to the Checklist to be completed

https://docs.google.com/spreadsheets/d/1pwft6r0YzIIEUaT8KfKKMguYpQpgp1e7/edit?usp=sharing&ouid=101935984536383661546&rtpof=true&sd=true

### Deployment

The Deployment phase involves executing the Cutover Plan, which ensures a smooth transition from the current state to the new system or solution. This critical phase is broken into three key components:

- Pre-Deployment Steps:

  - Final system checks and readiness validations.

  - Communication to stakeholders about the deployment timeline and any expected downtimes.

  - Backup of existing systems and data.

  - Final review and approval of deployment tasks with key stakeholders.

- Deployment Steps:

  - Execution of the cutover tasks as outlined in the plan.

  - Migration or activation of system components.

  - Validation of critical functionalities immediately post-deployment.

  - Troubleshooting and addressing any issues that arise during the deployment window.

- Post-Deployment Steps:

  - Comprehensive validation of the deployed system (smoke testing, sanity testing).

  - Monitoring system performance and resolving post-deployment issues.

  - Final sign-off from stakeholders after confirming system stability.

  - Handover of the deployed solution to operations or support teams, including relevant documentation.

By following the structured Cutover Plan, we ensure minimal disruption, successful deployment, and seamless adoption of the solution.

4o

## Go Live

### Go Live Preparation

    - Review the Production Smoke Test cases identified by the QA team

    - Identify the data setup and access required for conducting the Production smoke test

    - Coordinate with the customer on the smoke testing requirements from the customer end.

    - Deployment Tracker - Production Deployment

Link to the Checklist to be completed

https://docs.google.com/spreadsheets/d/1q-MtmyFXa1isSzC51wiusqfpy7iKFAfZe3PxDtXhyK4/edit?usp=sharing

### During Go-Live

    - Execute the Production Smoke Test cases identified. Typically the ones to be executed by the customer should be covered.

    - Report any issues Identified to the Project team for tracking & resolution.

    - Ø  End-User Training

    - Ø  Execute Deployment checklist

    - Ø  Setup Post Production Support

    - Gain formal signoff: Upon completion of the project, gain formal signoff from client for Project Closure

    - Deliverables:

      - Completed Deployment Checklist: The completed Production deployment activity checklist with detailed documentation of what was deployed.

      - Final User Manuals: The training program may include student manuals, instructor guides, application maintenance manuals and presentation materials for each course defined during the Design and Develop phases.

      - Final Client Acceptance signoff: Prior to closing the project, the project team reviews the results of the project and identifies improvements for future development projects. Team performance is evaluated, and project deliverables are filed.

### Post Go-Live

    - Help in the preparation of  the project artifacts to be handed over to the customer.

    - Handover the project related documentation for the Internal processes to the Solutions COE.

    - CSAT:

- Salesforce CSAT from partner portal:

CSAT Survey Link

- Conga, Oracle Forsys CSAT

10.4 Support/Hypercare

The Support/Hypercare phase is a critical period following deployment, ensuring the solution operates as intended and addressing any issues that may arise during the transition to regular operations. This phase includes the following components:

- Issue Reporting and Tracking:

  - Establish a centralized platform (Jira or Google Sheets) for reporting and tracking issues.

  - Define clear guidelines for issue logging, including priority levels and required details for faster resolution.

  - Assign ownership for monitoring and updating the issue tracker.

- Defect Triaging Calls:

  - Schedule regular triaging calls to review and prioritize reported defects.

  - Collaborate with stakeholders, technical teams, and end-users to determine resolution timelines.

  - Ensure transparency by sharing meeting notes and updated issue statuses with relevant stakeholders.

- Resolution of Issues:

  - Categorize issues into immediate fixes, post-hypercare enhancements, or future releases.

  - Implement and test resolutions in alignment with change management protocols.

- Monitoring System Performance:

  - Continuously monitor system metrics to identify and address performance or operational anomalies.

  - Share daily or weekly status reports summarizing the health of the deployed system.

- Knowledge Transfer and Training:

  - Conduct knowledge transfer sessions for support teams to ensure they can handle recurring tasks or minor issues independently.

  - Provide end-user training or refreshers to address common challenges.

- Project Closure Report:

  - Prepare and deliver a comprehensive Project Closure Report summarizing:

    - Deployment outcomes and key achievements.

    - Issues reported and their resolution status.

    - Recommendations for long-term improvements or future phases.

  - Obtain final sign-off from stakeholders, marking the transition to steady-state operations.

By thoroughly managing the Support/Hypercare phase, we ensure a seamless transition, high user satisfaction, and a successful project conclusion.

Link to Project Closure Template

## Training, Skills and Additional Content for a BA

Link to the documentation

12. Project Manager Responsibility – Contractor and PO Management

Project Managers are responsible for monitoring contractor engagement and Purchase Orders (POs) associated with the project. PMs should:

- Regularly check if contractors are nearing their contract expiry date. If an extension is required, they must reach out to the TAG and Finance teams to initiate the renewal process.

- Proactively monitor the expiry dates of POs and inform the Managing Director (MD) of the project well in advance to ensure timely PO extensions.

This ensures uninterrupted resource availability and financial alignment for project continuity.