## Sheet1
o | Template Description | Phase | Activity Type | Format | Internal/ External | Url Linked | Jeffin's Comments | BU Comments | Current | Old | links
1 | Playbook |  |  |  | Internal | https://docs.google.com/document/d/14imTpgjj9GDNL41IRUCYuXMRkxyU7BW2/edit#heading=h.gjdgxses |  |  |  |  | https://docs.google.com/document/d/14imTpgjj9GDNL41IRUCYuXMRkxyU7BW2/edit#heading=h.gjdgxses
2 | Create Kick - Off Deck (*Pitch deck) | Discovery/Preplanning | Task | Slide | External | Yes | Template required. Attached template is correct |  |  |  | https://docs.google.com/presentation/d/102UjksF2wECR_i49zz0bmnQ--ZdJUSkBZ0vZ7JTND5o/edit#slide=id.p1
3 | Communication Cadence Plan | Discovery/Preplanning | Task | Sheet | Internal | Yes | Template requierd. I have added new link to the template |  |  |  | https://docs.google.com/spreadsheets/d/1qBa64fnGscrGKXvgDYBd11SMTFXrFbVU/edit#gid=1147869503
4 | RAID Log Creation | Discovery/Preplanning | Task | Sheet | Internal+External | Yes | Template required. Attached template is correct |  |  |  | https://docs.google.com/spreadsheets/d/1lVgg359_gMBeyqy3g7uJyoH3aFcbfxil/edit#gid=1972975287
5 | RACI Sheet Creation | Discovery/Preplanning | Task | Sheet | Internal+External | Yes | Template required. Attached template is correct |  |  |  | https://docs.google.com/spreadsheets/d/1k5H4WKXADLrwpLTZIi641WfCGkheuvScLCxrqPQNI1A/edit?gid=1291000494#gid=1291000494
6 | JIRA Process Document | Discovery/Preplanning | Task | Slide | Internal+External | Yes | Not required for CDO |  |  |  | https://docs.google.com/presentation/d/1u4jNu_omwJLIBrp7hLV0_3uOkdqQknRd/edit#slide=id.p1
7 | Project High-level Plan Template | Discovery/Preplanning | Task | Smartsheet | Internal+External | Yes | Template required. Attached template is correct |  |  |  | https://app.smartsheet.com/sheets/Mrx9RJGM7438GCmJXgwrrFQX7fHGwHRV8qH99341?view=gantt
8 | Project High-level Plan Template | Discovery/Preplanning | Task | Sheet | Internal+External | Yes |  |  |  |  | https://docs.google.com/spreadsheets/d/1Put6HIT7a6wd5zevBndP_-_QtpTboFRY/edit#gid=217325727
9 | Create RTM | Define | Task | Sheet | Internal | Yes | low priority. Good to have |  |  |  | https://docs.google.com/spreadsheets/d/1WBqXG8acr9qmZWMm2zVp-LvHkIFdwYMAXotcNE70O54/edit#gid=0
10 | Maintain the MOM tracker | All | Task | Sheet | Internal+External | Yes | Required. Template needs to be changed |  |  |  | https://docs.google.com/document/d/10_lbo5MAHupoTovnFyaivi77pD38LnPJ/edit
11 | Test Stratergy and Exit & Entry Criterias to be Defined | Define | Task | Slide | Internal+External | Yes | Required. Check with Akshay on the correct template |  |  |  | https://docs.google.com/presentation/d/1qcRrns1EErqwVVk2T_lD9gyRc_c4v-WsSZyk3V0aAU0/edit#slide=id.g70ff1e5935_0_0
12 | Get the UAT Test Scenarios from Customer | Define | Task | Slide | External | Yes | Required. Check with Akshay on the correct template |  |  |  | https://docs.google.com/presentation/d/1jUMbvBrbg5ln40wNKO1ulPs8xM7wiXu17HmXVuhuwQ0/edit#slide=id.g8130db1483_1_309
13 | Provide Requirements Logical Grouping for Implementation & Sequence of Implementation and Dependancies to be called out (User stories ) | Design | Meeting | Sheet | Internal | Yes | Template required. |  |  |  | https://docs.google.com/spreadsheets/d/1C2pU8u19XqpToVSuNzVhwtmJu9XG86TFzx5aMjL1Dvw/edit#gid=0
14 | Define High level Test Scenarios | Design | Task | Sheet | Internal | Yes | Required. Check with Akshay on the correct template |  |  |  | https://docs.google.com/spreadsheets/d/1oBthsPd581JVUOizhCAUa_1l1XfwKTanzsfe-Pp8EQI/edit#gid=0
15 | Create the corresponding Workbook (CLM and/or CPQ,E-Comm , Salesforce, if Data Migration is in Scope Data Migration DataDictoionary execution sheet) which is compliant with the checklist | Design | Task | Sheet | Internal | TBD | template not required
16 | Create Configuration Log for the project | Build | Task | Sheet | Internal+External | Yes | Template required. |  |  |  | https://docs.google.com/spreadsheets/d/16SyGK9XJYGj6TNF1_9povZtaSYr1822PPk2R3I3-JQU/edit#gid=1030167411
17 | Gate Review | Design | Check point | Sheet | Internal | Yes | Template required. |  |  |  | https://docs.google.com/spreadsheets/d/1AGnNWXvcH6dJ4EjUZZOOhUL_Q31FYemr/edit#gid=185690352
18 | Authoring test Cases | Build | Task | Sheet | Internal | Yes | Required. Check with Akshay on the correct template |  |  |  | https://docs.google.com/spreadsheets/d/1oBthsPd581JVUOizhCAUa_1l1XfwKTanzsfe-Pp8EQI/edit#gid=0
19 | Share the release notes with Team (Managed Service project) | Build | Task | Sheet | Internal | Yes | Template required. Attached template is correct |  |  |  | https://docs.google.com/spreadsheets/d/1ZAMOM_gBXriZ4GgZ1aB1_SDhBMnhuFJ0/edit#gid=356534034
20 | Document the Issues Identified as Defects with RCA for Cutoverplan check-list | Build | Task | Sheet | Internal+External | Yes | Required. Check with Akshay on the correct template |  |  |  | https://docs.google.com/spreadsheets/d/1e517mhQxQ1Q1Tt7oUTmzAnRbE0jwpAOL/edit?gid=387487135#gid=387487135
21 | SMoke test in QA Post every Deployment | Build | Task | Sheet | Internal | Yes | Required. Check with Akshay on the correct template |  |  |  | https://docs.google.com/document/d/1Yr1_jQfrAEhSOEqki7Qny6Zi5Sk6NjI0/edit#heading=h.1fob9te
22 | Daily : Status Report During Build entire team (Including Customer) | Build | Task | Sheet | Internal+External | Yes | low priority. Good to have |  |  |  | https://docs.google.com/spreadsheets/d/1E_88wx6oxuHX6xeecxSOQfbfRIzcMj0sQm06uMDD7v0/edit#gid=0
23 | Track Test Cases result (dashboard with cases, RCA) | SIT | Task | Sheet | Internal+External | Yes | Required. Check with Akshay on the correct template |  |  |  | https://docs.google.com/spreadsheets/d/1yO9GQRY6P2guM3EBsF4c3n05tTDZ2I1M/edit#gid=1059985200
24 | Daily : Status Report During SIT entire team (Including Customer) | SIT | Task | Sheet | Internal+External | Yes | Template required. Check with akshay on the correct template |  |  |  | https://docs.google.com/document/d/1RgxWm6BSl9fhouGiwCBS1UL40BzodalS1oRI3N5GAZE/edit
25 | Document and Share Lessons Learned (Internal) | Hypercare | Task | Sheet | Internal | Yes | Template not required, |  |  |  | https://docs.google.com/presentation/d/1UPuGGxeTMrsFOqNgyXUTP-8lxVBwfUdyduiqxerdJB8/edit#slide=id.g27312dfb732_0_1417
26 | Conduct Project Closure Debrief with Customer | Hypercare | Meeting | Sheet | External | Yes | Required. Atttached template is correct |  |  |  | https://docs.google.com/document/d/1w3J_JYjdIEbjt95OiLPu3WZh_OVH00c2/edit
27 | Cutover | UAT,Go-Live | Task | Sheet | External | Yes | Template required. |  |  |  | https://docs.google.com/spreadsheets/d/1NNZpLfshbbYNDnmg0ZnZ4wfTzKJrKEngdcsQmqjDW80/edit#gid=0
28 | ChangeOrderXX_(Application_Managed_Services)_SOW Name | Pre-Sales |  | Document | External | Yes | Template required. |  |  |  | https://docs.google.com/document/d/1eZvDibQ5VPnbYnpnA5Kv0srUz8IWegxj/edit
29 | ChangeOrderXX_(FixedBid)_Project_SOW Name | Pre-Sales |  | Document | External | Yes | Template required. |  |  |  | https://docs.google.com/document/d/156k_pUhOBI98K89DvWY6wXvTK1ecx3_n/edit
30 | ChangeOrderXX_(Capacity_Services)_SOW Name | Pre-Sales |  | Document | External | Yes | Template required. |  |  |  | https://docs.google.com/document/d/1-qUjMjfgWl8R3JpYfod15-0PPcKzt2Hs/edit
31 | ChangeOrderXX_(T&M)_Project_SOW Name | Pre-Sales |  | Document | External | Yes | Template required. |  |  |  | https://docs.google.com/document/d/1_AXKppCcz7X55ikeumcGgzUPYH75QlyD/edit
32 | Weekly Status Report | All |  | Slide | Internal+External | Yes | Template required. |  |  |  | https://docs.google.com/presentation/d/1PvXkZtwAh2UJ_wW3tF_e7tDpqbAufLShLkxGCH7ddl8/edit#slide=id.p1
33 | Esclation Matrix | All |  | Slide | Internal | Yes | Template not required. Part of Kick off |  |  |  | https://docs.google.com/presentation/d/1mtsvYkFe_Vnlng14O986xQ4XdJdTOaRZ/edit#slide=id.p1
34 | KPI baselining and measurement |  |  |  | Internal | Yes |  |  |  |  | https://docs.google.com/spreadsheets/d/1B8QBjihCvRY4Qah0uIOUJ05XKPPOO1OK/edit?gid=1437787652#gid=1437787652
35 | Burn Report | All |  |  |  | Yes |  |  |  |  | https://docs.google.com/spreadsheets/d/1E8dO9c6xytJwThLrX3j28v1Y4tObsoZh/edit?gid=1437787652#gid=1437787652

## Sheet2
RED | Template missing
orange | akshay
yellow | need to discuss