## Requirements Overview
Area | Overview
Go to Market | BDR and Sales are involved in the Go to Market. They mostly work on Direct Sales and today they are not having any partner or other areas where they do the sales US based and one sales rep is in Canada | 40 Sales Rep - Direct Sales Inside sales Team - 5 Member team they work on Add On Services
Investment summary is created in xls and it is used to generate both the quote and contact. (XLS with Macros and VBA)
IMS is used to populate the Core products, modules, Integrations, Addon Services, Billable Hours etc.
It also support in Commission calculation for Sales
It create a list of item for internal processing so that XLS will feed in to Netsuite for Ordering and Invoicing
Persona | BDR Sales Reps - 40 Inside Sales - 5 Sales Operations (Contract Management) Legal (Red lining) Finance
Quote Life Cycle | Opportunity (Create in Netsuite) - Opportunity Line item are created once the Contract is signed. Investment Summary (XLS) - Help us to create the Quote and generate the Contract. Generate Contract button in Investment summary Sharepoint Folder - For all the document repository, they create the folder structure to support the same. Docusign +Netsuite - For esignature of the Contract Order (NetSuite) - Once the Opportunity lines are created, then they create the Order Invoicing (NetSuite) - Part of the process, the invoices will be create in NetSuite | Amendement (Upgrade) - Version upgrade of the Software. Investment Summary Core xls is update every week, they have a whole new investment summary each time they need to quote to a customer. If they need to quote, they need to pull it from NetSuite and update the xls with the updated details | Renewals - They have a lead management team, they keep a track of Contract which are due for Renewals. Typical Sales Cycle is for 3 Years, Investment summary is used to do a Renewal. A completely new Investment summary is created for the Current Market Price
Product Life Cycle | New product introduction - Regural new product introduction is not in place, they have regural Core products (load master, power broker, or document power) Combination of these Services. Version Control : Version Control is in place for these products and they upgrade is based on the Version Update | Total Products - Less than 700 Sku, which include Core Products, Services, Add-on and Integration Core Products. - (LoadMaster and PowerBroker DocumentPower) Services are offered in Turnkey Proposal when the users are limited like 50 Users etc. If its Enterprise level then the Calcualtion will come in picture like Hourly basis etc. Services are auto populated Addon - They are manually selected by the Users Quote Size - For a Core product like Load Master & Document Power - If it can be configured as a Bunle it can be upto 50-70 (Core - 5-8 Products, then Services, Addons etc) Lineitems on the Cart. | Product Category - Base Imaging LTL Other Mobile App | Product Type - Interface Base Software Module User License Document Power Base Module Services Training Support & Maintenance Third Party Software User Conference | Item Category License - Perpetual License - Term Services Support - New Training Maintenance - New Other | Product Line LoadMaster and PowerBroker DocumentPower None LoadMaster PowerBroker EDI LoadMaster LTL LoadMaster, LoadMaster LTL, and PowerBroker McLeod IQ Professional Services McLeod Anywhere Training Other LoadMaster, LoadMaster LTL, and PowerBroker, DocumentPower
Pricing Overview | USD Pricing - one US pricelist. Pricing Changes are handle twice a year. | - Core Products are Perpetual today. - Service pricing is based on Number of Users (Tiered Pricing) - Planning to introduce Subscription based pricing, today most of the pricing is Perpetual - Service Pricing is Rate Per Hour for specific Add-Ons - They have Uplift for each year, but the uplift % is not determined ahead and its determined on completing of first year. (3% to 5%)
Discounting | Services are never discounted. Line item discount - Ocassitionaly Quote Level Discounts - excludes Services Non Discounted Products Certain Promotions - Like Free Trail for first 3 Months Empowered Discounts TIA Discounts - If you belong to this program you get discounts
Approvals | Approvals are discounts go hand in Hand. Sales will have certain discounts, Manager will have next level and Vp Level discounting approvals Approvals are sequential

## Estimates
Phase | Activities Included | Volume | Hours / Unit | Estimated Hours | Phase-wise Hours Total
Plan & Define (Requirement Gathering) | Project Plan, Milestones Workshops Detailed Scoping & Requirement Document Review & Revision | 1 | 80 | 80 | 80
Designing | Create Product Layout, rules, Validations, Opportunity Management,Quote Management | 1 | 120 | 120 | 120
Project Communication | Meetings / Conf Calls / Demo / Review / MoM | 1 | 160 | 160 | 160
Build | Quote Workflow (New, Amendments & Renewals) | 3 | 16 | 48 | 731.5
| Product Setup - Standalone (Field Creation, Page Layouts, 2 Pricelists, Permissions, Revenue & Billing fields) | 750 | 0.25 | 187.5
| Product Setup - Bundles (Field Creation, Page Layouts, 2 Pricelists, Permissions, Revenue & Billing fields) | 4 | 40 | 160
| Product Rules | 100 | 0.5 | 50
| Additional Pricelists (Contract Pricelists) | 15 | 2 | 30
| Pricing Rules | 80 | 2 | 160
| Approvals (Salesforce 3 Levels) - Process Builder / Flows | 3 | 8 | 24
| Templates (1 Order Forms - English Only) | 2 | 16 | 32
| CPQ Package Settings | 1 | 40 | 40
QA | Test Strategy Test Execution Bug Fixes | 1 | 80 | 80 | 80
UAT | Support including feedback incorporation & UAT Fixes | 1 | 80 | 80 | 80
Go-Live & Production Support | Deployment Training & Documentation Support 2 wk Support Query Resolution, Bug Fixes User Support & Adoption Facilitation | 1 | 80 | 80 | 80
Total Hours |  |  |  |  | 1331.5

## Plan+Offshore+Onsite
McLeod CPQ Conga Platform Estimates (NetSuite + Standalone Conga Platform)
[6 empty] | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18
Plan/Define
Design
[10 empty] | Sprint 1 |  | Sprint 2 |  | Sprint 3 |  | Sprint 4
QA
UAT
[22 empty] | Go Live | Hyper Care
Role | Level | Rate | Status | Cost | Total Cost | [18 empty] | Total Hours | Total Price
Project Manager(PM) | L5 | 173 | Onshore | 94 | 41360 | 40 | 40 | 40 | 40 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 440 | 76120
CPQ SA | L3 | 189 | Onshore | 88 | 37840 | 40 | 40 | 40 | 40 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 10 | 430 | 81270
CPQ BA | L4 | 158 | Onshore | 88 | 61600 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 20 | 700 | 110600
Integration Dev | L4 | 50 | Offshore | 22 | 5280 | W9: 40; W10: 40; W11: 40; W12: 40; W13: 20; W14: 20; W15: 20; W16: 20 | 240 | 12000
Data Migration Eng | L4 | 50 | Offshore | 22 | 5280 | W9: 40; W10: 40; W11: 40; W12: 40; W13: 20; W14: 20; W15: 20; W16: 20 | 240 | 12000
Config Eng | L3 | 44 | Offshore | 16 | 7680 |  |  |  |  | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 20 | 20 | 20 | 20 | 480 | 21120
CPQ Dev | L4 | 50 | Offshore | 22 | 6160 |  |  |  |  | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 280 | 14000
QA Eng | L3 | 44 | Offshore | 16 | 3200 | W11: 20; W12: 20; W13: 40; W14: 40; W15: 40; W16: 40 | 200 | 8800
[5 empty] | 168400 | [18 empty] | 3010 | 335910
49.87%
[5 empty] | 44.3% | [18 empty] | 10% | 302319
[5 empty] | 37.33% | [18 empty] | 20% | 268728

## Deck-plan
W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16
Plan/Define
Design
|  |  |  | Sprint 1 |  | Sprint 2 |  | Sprint 3
QA
UAT
[14 empty] | Go Live | Hyper Care

## Offshore+PM-Onshore-Plan
McLeod CPQ Conga Platform Estimates (NetSuite + Standalone Conga Platform)
[6 empty] | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18
Plan/Define
Design
[10 empty] | Sprint 1 |  | Sprint 2 |  | Sprint 3 |  | Sprint 4
QA
UAT
[22 empty] | Go Live | Hyper Care
Role | Level | Rate | Status | Cost | Total Cost | [18 empty] | Total Hours | Total Price
Project Manager(PM) | L5 | 55 | Onsite | 43 | 18920 | 40 | 40 | 40 | 40 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 440 | 24200
CPQ SA | L3 | 189 | Offshore | 88 | 37840 | 40 | 40 | 40 | 40 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 10 | 430 | 81270
CPQ BA | L4 | 83 | Offshore | 59 | 41300 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 20 | 700 | 58100
Integration Lead | L5 | 55 | Offshore | 27 | 6480 | W9: 40; W10: 40; W11: 40; W12: 40; W13: 20; W14: 20; W15: 20; W16: 20 | 240 | 13200
Data Migration Lead | L5 | 55 | Offshore | 27 | 6480 | W9: 40; W10: 40; W11: 40; W12: 40; W13: 20; W14: 20; W15: 20; W16: 20 | 240 | 13200
Config Eng | L3 | 44 | Offshore | 16 | 7680 |  |  |  |  | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 20 | 20 | 20 | 20 | 480 | 21120
CPQ Dev | L5 | 55 | Offshore | 27 | 7560 |  |  |  |  | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 280 | 15400
QA Lead | L5 | 55 | Offshore | 27 | 5400 | W11: 20; W12: 20; W13: 40; W14: 40; W15: 40; W16: 40 | 200 | 11000
[5 empty] | 131660 | [18 empty] | 3010 | 237490
44.56%
180 -230

## CLM-Offshore+PM-Onshore-Plan
McLeod CPQ Conga Platform Estimates (NetSuite + Standalone Conga Platform)
[6 empty] | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18
Plan/Define
Design
[10 empty] | Sprint 1 |  | Sprint 2 |  | Sprint 3 |  | Sprint 4
QA
UAT
[22 empty] | Go Live | Hyper Care
Role | Level | Rate | Status | Cost | Total Cost | [18 empty] | Total Hours | Total Price
Project Manager(PM) | L5 | 55 | Onsite | 43 | 18920 | 40 | 40 | 40 | 40 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 440 | 24200
CPQ SA | L3 | 189 | Offshore | 88 | 37840 | 40 | 40 | 40 | 40 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 10 | 430 | 81270
CPQ BA | L4 | 83 | Offshore | 59 | 41300 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 20 | 700 | 58100
Integration Lead | L5 | 55 | Offshore | 27 | 6480 | W9: 40; W10: 40; W11: 40; W12: 40; W13: 20; W14: 20; W15: 20; W16: 20 | 240 | 13200
Data Migration Lead | L5 | 55 | Offshore | 27 | 6480 | W9: 40; W10: 40; W11: 40; W12: 40; W13: 20; W14: 20; W15: 20; W16: 20 | 240 | 13200
Config Eng | L3 | 44 | Offshore | 16 | 7680 |  |  |  |  | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 20 | 20 | 20 | 20 | 480 | 21120
CPQ Dev | L5 | 55 | Offshore | 27 | 7560 |  |  |  |  | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 280 | 15400
QA Lead | L5 | 55 | Offshore | 27 | 5400 | W11: 20; W12: 20; W13: 40; W14: 40; W15: 40; W16: 40 | 200 | 11000
[5 empty] | 131660 | [18 empty] | 3010 | 237490
44.56%
180 -230

## All Offshore wo Integration Pla
McLeod CPQ Conga Platform Estimates (NetSuite + Standalone Conga Platform)
[6 empty] | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16
Plan/Define
Design
[10 empty] | Sprint 1 |  | Sprint 2 |  | Sprint 3
QA
UAT
[20 empty] | Go Live | Hyper Care
Role | Level | Rate | Status | Cost | Total Cost | [16 empty] | Total Hours | Total Price
Project Manager(PM) | L5 | 55 | Onsite | 43 | 17200 | 40 | 40 | 40 | 40 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 400 | 22000
CPQ SA | L3 | 66 | Offshore | 43 | 16770 | 40 | 40 | 40 | 40 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 10 | 390 | 25740
CPQ BA | L4 | 83 | Offshore | 59 | 36580 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 20 | 620 | 51460
Data Migration Eng | L4 | 50 | Offshore | 22 | 5280 | W7: 40; W8: 40; W9: 40; W10: 40; W11: 20; W12: 20; W13: 20; W14: 20 | 240 | 12000
Config Eng | L3 | 44 | Offshore | 16 | 6400 |  |  |  |  | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 20 | 20 | 20 | 20 | 400 | 17600
CPQ Dev | L4 | 50 | Offshore | 22 | 5280 |  |  |  |  | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 240 | 12000
QA | L2 | 39 | Offshore | 11 | 2200 | W9: 20; W10: 20; W11: 40; W12: 40; W13: 40; W14: 40 | 200 | 7800
[5 empty] | 89710 | [16 empty] | 2490 | 148600
39.63%
180 -230

## CLM-All Offshore wo Integration
McLeod CLM Conga Platform Estimates
[6 empty] | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18
Plan/Define
Design
[10 empty] | Sprint 1 |  | Sprint 2 |  | Sprint 3 |  | Sprint 4
QA
UAT
[22 empty] | Go Live | Hyper Care
Role | Level | Rate | Status | Cost | Total Cost | [18 empty] | Total Hours | Total Price
Project Manager(PM) | L5 | 55 | Offshore | 43 | 15480 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 360 | 19800
CLM SA | L3 | 66 | Offshore | 43 | 18490 | 40 | 40 | 40 | 40 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 10 | 430 | 28380
CLM BA | L4 | 55 | Offshore | 38 | 26600 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 20 | 700 | 38500
Config Eng | L4 | 50 | Offshore | 22 | 8800 |  |  |  |  | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 20 | 20 | 20 | 20 |  |  | 400 | 20000
CLM Dev | L3 | 44 | Offshore | 16 | 7680 |  |  |  |  | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 20 | 20 | 20 | 20 | 480 | 21120
CLM Dev | L3 | 44 | Offshore | 16 | 4480 |  |  |  |  | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 280 | 12320
QA | L2 | 39 | Offshore | 11 | 2640 | W9: 20; W10: 20; W11: 20; W12: 20; W13: 40; W14: 40; W15: 40; W16: 40 | 240 | 9360
[5 empty] | 84170 | [18 empty] | 2890 | 149480
43.69%
[5 empty] | 37.43% | [18 empty] | 10% | 134532

## All Offshore wIntegration Plan
McLeod CPQ Conga Platform Estimates (NetSuite + Standalone Conga Platform)
[6 empty] | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18
Plan/Define
Design
[10 empty] | Sprint 1 |  | Sprint 2 |  | Sprint 3 |  | Sprint 4
QA
UAT
[22 empty] | Go Live | Hyper Care
Role | Level | Rate | Status | Cost | Total Cost | [18 empty] | Total Hours | Total Price
Project Manager(PM) | L5 | 55 | Onsite | 43 | 18920 | 40 | 40 | 40 | 40 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 440 | 24200
CPQ SA | L3 | 66 | Offshore | 43 | 18490 | 40 | 40 | 40 | 40 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 10 | 430 | 28380
CPQ BA | L4 | 83 | Offshore | 59 | 41300 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 20 | 700 | 58100
Integration Lead | L5 | 55 | Offshore | 27 | 6480 | W9: 40; W10: 40; W11: 40; W12: 40; W13: 20; W14: 20; W15: 20; W16: 20 | 240 | 13200
Data Migration Lead | L5 | 55 | Offshore | 27 | 6480 | W9: 40; W10: 40; W11: 40; W12: 40; W13: 20; W14: 20; W15: 20; W16: 20 | 240 | 13200
Config Eng | L3 | 44 | Offshore | 16 | 7680 |  |  |  |  | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 20 | 20 | 20 | 20 | 480 | 21120
CPQ Dev | L5 | 55 | Offshore | 27 | 7560 |  |  |  |  | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 280 | 15400
QA Lead | L5 | 55 | Offshore | 27 | 5400 | W11: 20; W12: 20; W13: 40; W14: 40; W15: 40; W16: 40 | 200 | 11000
[5 empty] | 112310 | [18 empty] | 3010 | 184600
39.16%
180 -230