## Sheet1
Sprint | Start Date | End Date
Sprint-3 | 2025-12-08 | 2025-12-19
Overall Stories | CPQ | CLM | DM | DI |  | Current Dependedent Stories for Sprint 3 | Salesforce | Digicert
223 | 135 | 81 | 5 | 2 |  |  | 14 | 8
Build Completed Sprint-0 | 4 | 13 | 0 | 0
Build Completed Sprint-1 | 28 | 11 | 0 | 0
Build Completed Sprint-2 | 19 | 19 | 0 | 0
Overall Completed Till date | 51 | 43 | 0 | 0 | 94
Sprint-3
Track | Planned | Completed | Move to Next Sprint | Completion Rate | Inprogress | Comments
CPQ | 33
CLM | 39 |  |  |  |  | 6 User Stories are open for the AC writing and closure which will be completed after the demo this week. Rest other user stories SD will be completed this week.
DM | 5
DI | 2
79
Sprint-4 | Approx 50-60 User Stories if all taken in the next build sprint

## RCA Sprint-3 (Jira)
Issue Type | Issue key | Summary | Parent key | Parent summary | Sprint | Status | Assignee | Due Date | Dependency On | Comments
Story | RCA-1222 | Quote start date' to be defaulted based on the minimum start date of all quote lines and 'Quote end date' field to be defaulted based on the maximum of all end dates on the quote lines. | RCA-34 | Quote Management | Sprint-3 | Unit Testing in progress | Jayaprakash & Prasanth | 12/12/2025 12/13/2025 12/15/2025 |  | 12/11 : Build will be completed by today and will start unit testing tomorrow 12/12 : Need to complete by 13th Dec (Jayaprakash) 12/15 : Unit Testing needs to be completed
Story | RCA-1221 | Need 'Request BD/Legal Help' action on the quote to capture Additional T&C requested by customer | RCA-34 | Quote Management | Sprint-3 | Unit Testing in progress | Srilekha | 12/13/2025 12/15/2025 |  | Need some clarification on this ( need to discuss with nagalakshmi) 09-Dec - On Sick leave 10-Dec - Had a discussion with mahalakshmi (Case management part need to check with Neelima) rest build will start today 10-Dec - Neelima will update the solution document and Sriliekha will connect with Ramesh for any question 11-Dec - Rohit to share the user details in the queue from digicert 12-Dec -Details are shared and need to complete the build. 15-Dec - JIRA needs to update
Story | RCA-576 | As a Sales/Legal/Business Desk user I want to create a Order Form contract record, linked to a Quote or New/existing Account. | RCA-28 | CLM | Sprint-3 | Build completed | Srinivas T, Karthik | 2025-12-11
Story | RCA-556 | Create Asset Line item fields | RCA-34 | Quote Management | Sprint-3 | Open | Srilekha | TBD |  | 09-Dec - On Sick leave 10-Dec - Mapping of the Conga CPQ to RCA is required 11-Dec - Analysis in progress 12-Dec - Analysis and discussion with Maha and Chaitali will complete today. 15-Dec - Shared file with Maha and Chaitali and need to disccuss with them today
Story | RCA-485 | Ability for the business team to send the final document using Docusign for e-Signatures or manually for wet signature based upon the signer information provided by requester during the agreement request. | RCA-28 | CLM | Sprint-3 | Open | Mahalakshmi | 2025-12-16 |  | 15-Dec - Will try to close this today.
Story | RCA-425 | As a Sales user I should be able to select the values in the clause type "Negotiated MSA Tie-In" picklist field on the quote before generating the proposal document. | RCA-28 | CLM | Sprint-3 | Unit Testing in progress | Mahalakshmi / Karthik | 12/11/2025 12/12/2025 12/15/2025 | Salesforce | Dependency : Wet signature functionality is there in RCA or not.
Story | RCA-424 | As a Sales user I should be able to select the values in the clause type "Auto Renewal" picklist field on the quote before generating the proposal document. | RCA-28 | CLM | Sprint-3 | Build completed | Karthik | 2025-12-11
Story | RCA-423 | As a Sales user I should be able to generate the proposal document (Order form) for Partners based on the contract type as " Per Cert (Pay go)". | RCA-28 | CLM | Sprint-3 | Build completed | Srinivas T | 2025-12-10 |  | Dependency on RCA-102 for the closure 10-Dec - Unit Testing needs to be done today
Story | RCA-422 | As a Sales user I should be able to generate the proposal document (Order form) for Partners based on the contract type as " Per Cert (Ongoing)". | RCA-28 | CLM | Sprint-3 | Build completed | Srinivas T | 2025-12-10 |  | Dependency on RCA-102 for the closure 10-Dec - Unit Testing needs to be done today
Story | RCA-421 | As a Sales user I should be able to generate the proposal document (Order form) for Partners based on the contract type as " Bulk Dollar (Standard)". | RCA-28 | CLM | Sprint-3 | Build completed | Srinivas T | 2025-12-10 |  | Dependency on RCA-102 for the closure 10-Dec - Unit Testing needs to be done today
Story | RCA-420 | As a Sales user I should be able to generate the proposal document (Order form) based on the contract type as " ELA". | RCA-28 | CLM | Sprint-3 | Build completed | Srinivas T | 2025-12-10 |  | Dependency on RCA-102 for the closure 10-Dec - Unit Testing needs to be done today
Story | RCA-419 | As a Sales user I should be able to generate the proposal document (Order form) based on the contract type as " Subscription". | RCA-28 | CLM | Sprint-3 | Build completed | Karthik | 2025-12-10 |  | Dependency on RCA-102 for the closure 10-Dec - Unit Testing needs to be done today
Story | RCA-418 | As a Sales user I should be able to generate the proposal document (Order form) based on the contract type as " Flat Fee". | RCA-28 | CLM | Sprint-3 | Build completed | Karthik | 2025-12-10 |  | Dependency on RCA-102 for the closure 10-Dec - Unit Testing needs to be done today
Story | RCA-410 | Inbound integrations from Netsuite to RCA | RCA-26 | Integration | Sprint-3 | Open | Pramod | TBD | Digicert, Neelima , Ramesh | Dependency : 1- RCA-1162 :Fields need to be created in the RCA object (Orders & Assets) Inbound & Outbound Fields need to be created. Pramod is in discussion with Ramesh for these fields. Note : Current focus on the Available fields only in RCA. 08-Dec - Neelima and Ramesh will discuss with Digicert today for the open questions 09-Dec - Total SOQL for Outbounds - 8 given by Digicert, all need to be set for the RCA. In discussion with Digicert for each individual SOQL is divided into 2 or more SOQL - Confirmantion pending Note : No SOQL for Inbounds 10-Dec - Agreed by Digicert on the above request. Need to share the MOM of the agreement with Digicert. Team is working on the Split of SOQL SOQL is not applicable here 11-DEC - MOM has been shared. Pramod needs to review the created fields for the Order and Order Line Items created till the time.Only this task is open for the Inbound. 12-Dec - Order Fields - In Source Apttus, over 200 fields, need to check in the RCA system how many fields are there is created.
Story | RCA-383 | Process for marking an order as canceled (after booking) | RCA-35 | Order Management | Sprint-3 | On Hold | Akash | TBD | Neelima , Rohit | 08-DEC - Sheshma is on Sick leave today 09-Dec - Order Flow needs to clear after booking scenarios. Solution needs to be finalized and need to discuss again with Digicert for the confirmation - ETA - 10th Dec 10-Dec - AC & SDD will update today. 11-Dec - Review is in progress with Digicet but team can start in parallel 12-Dec - Assigned to Akash and Maha will connect to provide the walkthrough what needs to be done. SDD needs to be provided - 15-Dec
Story | RCA-375 | Process for marking an order as 'Problem Order' (before booking) | RCA-35 | Order Management | Sprint-3 | Open | Sheshma | TBD |  | 08-Dec - Sheshma is on Sick leave today 09-Dec - Need to conenct with Ramesh in the absence of Nagalakshmi today Solution Design needs to update - ETA- 9th Dec'25 10-Dec - Changes are there in the AC, so team will provide the updated AC and Solution 10-Dec - AC & SDD will update today. 12-Dec - Neelima connected with Sheshma and explained what atleast can start with but the AC and Sol is open. Tech discussion needed with Ramesh 15-Dec - Sheshma will start the build and confirm the ETA.
Story | RCA-374 | Giving access to the Sales Rep for the order field updates | RCA-35 | Order Management | Sprint-3 | Open | Bittu | 12/09/2025 12/11/2025 12/12/2025 12/15/2025 |  | 08-DEC - If the approval process task will complete today then it will be completed by tomorrow otherwise on Wednesday 09-Dec- Need to conenct with Ramesh in the absence of Nagalakshmi today 10-Dec - Tech discussion happened with Ramesh and the approch was told to proceed. 12-Dec - Tech Approach is changed, now going with the LWC by Ramesh. This will be completed today 15-Dec - There is a change in the AC, now need to discuss with Maha and Chaitali.
Story | RCA-126 | Quote Acceptance | RCA-34 | Quote Management | Sprint-3 | Open | Jayaprakash, Shakthi | 2025-12-17 | Nagalakshmi | 08-Dec - Reviewing the Solution Document and will provide the ETA by EOD today 09-Dec - Need to update all the dependencies SDD needs to update - 9th Dec 10-Dec - SDD needs to update 12-Dec - SDD is updated and team started reviewing 15-Dec - Need to discuss with Nagalakshmi on the tech approach
Story | RCA-75 | Quote Status: Define status and execution status fields on the quote object | RCA-34 | Quote Management | Sprint-3 | Open | Srilekha | 12/10/2025 12/12/2025 12/15/2025 |  | 08-Dec - Need to discuss with Nagalakshmi on the steps and then proceed for the changes 09-Dec - On Sick leave 10-Dec - Rohit will check the Excel file and provide the update 12-Dec - File is not yet updated by Rohit. 15-Dec - This will be closed today
Story | RCA-161 | As a Sales rep once the contract document is signed by the customer, I should be able to activate the Contract. | RCA-28 | CLM | Sprint-3 | Cancelled | Lakshmi Narayana | 2025-12-11 | Rohit , Neelima , Karthik V | 11-Dec : This will be merged in to order activation story and a new story will be created. Karthik needs to discuss with Neelima and Rohit. 12-Dec - Rohit will create the another user story and this will not be valid any more.
Story | RCA-59 | Setup backup admin for approval process | RCA-29 | Approval Management | Sprint-3 | Open | Subhashini, Jyothi Lanka | TBD | Neelima | 08-DEC - ETA will be updated by Harcharan after the analysis today 10-Dec - Assigned to Gaurav 11-Dec - Need to discuss with Nagalakshmi and take the approval on the complete implementation. 15-Dec - This feature is not available in RCA and need to discuss with Neelima for the further steps.
Story | RCA-65 | Auto reapprovals for discounts on price changes within a certain threshold | RCA-29 | Approval Management | Sprint-3 | On Hold | Mahitha & Gaurav | TBD | Salesforce | RCA-69 and RCA-65 having same solution OOTB Smart Approvals is not working. 05-Dec - Salesforce Case is raised by Mahitha #472143757 08-DEC - Waiting for the update from Salesforce
Story | RCA-251 | CPI' selection to drive specific clauses on the template | RCA-28 | CLM | Sprint-3 | Cancelled |  |  |  | Duplicate of RCA-133 , RCA-157. Updated in the JIRA
Story | RCA-329 | Clause librarary access restrictions | RCA-28 | CLM | Sprint-3 | Open | Karthik | 12/11/2025 12/12/2025 |  | 12-Dec- Karthik V needs to discuss with Karthik A and close this ticket today
Story | RCA-339 | Template permissions by role | RCA-28 | CLM | Sprint-3 | Build completed | Lakshmi Narayana | 2025-12-10
Story | RCA-342 | Audit log and field history tracking | RCA-33 | Security | Sprint-3 | Build completed | Shakthi | TBD |  | 08-Dec - Discussion required with Jayaprakash and then will confirm the ETA. 09-Dec - This story is done
Story | RCA-335 | Field-level security | RCA-33 | Security | Sprint-3 | On Hold | Ramesh & Nagalakshmi | TBD | Ramesh | 08-Dec - Need the Field Level Security Details for the implementation. 10-Dec - Need to go as is in the system.
Story | RCA-337 | Sharing Rules and role hierarchy | RCA-33 | Security | Sprint-3 | On Hold | Ramesh | TBD | Ramesh | 08-Dec - Sharing Rules and role hierarchy is required b/w BA's , SA's and Tech Arch. team. Need to discuss in the SA & BA call. 10-Dec - Ramesh needs to provide the fille to the DEV Team 10-Dec - Role hierarchy we need to maintain as it is. Ramesh will check for the unit testing
Story | RCA-324 | Profiles & Permission Sets for Sales, Legal, Admin, Order Management, Business Desk | RCA-33 | Security | Sprint-3 | On Hold | Shakthi | TBD | Ramesh | 08-Dec - Permission Set Discusson is required b/w BA's , SA's and Tech Arch. team. Need to discuss in the SA & BA call. 10-Dec - Ramesh needs to provide the fille to the DEV Team
Story | RCA-286 | Renewals opportunity to be created with the same contract type as the original deal | RCA-31 | Renewals/ABO | Sprint-3 | Build completed | Mahitha | 12/09/2025 12/10/2025 | Rohit | 09-Dec - On Track 10-Dec - Rohit needs to update the AC
Story | RCA-102 | Implement and manage the 'super quote' by combining the quote and order form into a single, dynamic document | RCA-28 | CLM | Sprint-3 | On Hold | Srinivas T, Karthik , Mahalakshmi | 2025-12-10 | Digicert (Lindsey) | On Track for 10th Dec US Timings closure 10-Dec - Missing language from Digicert.
Story | RCA-79 | System should support different start and end dates for individual lines with in a single quote | RCA-34 | Quote Management | Sprint-3 | Unit Testing in progress | Subhashini | 12/12/2025 12/15/2025 |  | Completed and Need to upload the document in JIRA.
Story | RCA-115 | Sync Signed Date from Order Form to Quote | RCA-28 | CLM | Sprint-3 | Open | Srinivas T | 12/11/2025 12/12/2025 | Karthik V | We need DocuSign for this and can be worked at a later point.
Story | RCA-112 | Update Quote Lines in Cart (mass update, and single-line edit) | RCA-34 | Quote Management | Sprint-3 | Build completed | Mahitha | 2025-12-05
Story | RCA-226 | Configure Product Visibility Rules | RCA-41 | Product Management | Sprint-3 | Unit Testing in progress | Akash | 12/09/2025 12/10/2025 12/12/2025 12/15/2025 |  | Validate and confirm if the RCA-225 and RCA-226 are same ? 08-Dec - Discuss with Chaitali and Maha for the function discussion 09-Dec - Discussion required with Tech Arch 10-Dec - Unit Test result needs to add. 12-Dec - Neelima needs the walkthrough of this user story 15-Dec - Need to add Unit test results in JIRA , need to check for the config log update
Story | RCA-227 | Configure Product Rules | RCA-41 | Product Management | Sprint-3 | On Hold | Akash, Bittu , Gaurav , Mahitha | TBD | Salesforce | Solution needed from Salesforce. 08-DEC - There is no update from the Salesforce
Story | RCA-224 | Consolidate SKU Master Catalog in RCA | RCA-41 | Product Management | Sprint-3 | On Hold | Akash | TBD | Salesforce | Only pending the testing of Constaint rules which are on hold currently Constraint Rules have a dependency on Salesforce.
Story | RCA-225 | Manage Product Lifecycle | RCA-41 | Product Management | Sprint-3 | Open | Gaurav | 12/12/2025 12/16/2025 | Mahitha | Conflict in the Sub task created and SDD. Need clarification from Neelima 09-Dec - Solution needs to be discuss with Neelima 10-Dec - Solution is updated and need to start the build. 11-Dec - Stuck somewhere in the workflow.Needs technical help. 15-Dec - Discussed with Mahitha and now working on the other approach to complete it.
Story | RCA-313 | Reps should be able to create a quote with zero pricing during the trial periods | RCA-36 | Pricing Management | Sprint-3 | Cancelled | Subhashini | 2025-12-10 | Digicert | Dependency is there..Need to provide business inputs -products - Which Product to create Trial Period 10-Dec - This story we are putting on hold and need to discuss with Neelima and Vinutha for the expected changes. 10-Dec - This story is under review with Digicert for the cancellation. If dogicert is asking to work then there is a dependencu on salesforce 11-Dec : RCA-313 (trial period) can be cancelled based on confirmation from DC
Story | RCA-322 | Enable pricing based on price type (Tiered, related pricing, list price etc.) | RCA-36 | Pricing Management | Sprint-3 | On Hold | Jyothi Lanka | 12-10-2025 12/15/2025 | Nagalakshmi , Neelima | Dependency : Technical Approach is required 12-Dec - Nagalakshmi needs to connect with Neelima 15-Dec - Need to connect with Nagalakshmi for the better understanding if anything related to build is open or the tech approach is correct. Need to add the Unit Test results.
Story | RCA-344 | Enable Use of Addendums to MSA/MRA for Seat-Based Contracts in Japan | RCA-28 | CLM | Sprint-3 | Open | TBD | TBD | Karthik V | 09-Dec - Need clarification 10-Dec - Need to discuss with Karthik V 10-Dec - We are not taking up the Japan contracts as of now.
Story | RCA-340 | Order Layout and Field Access | RCA-35 | Order Management | Sprint-3 | Open | Bittu | TBD | Digicert , Ramesh , Nagalakshmi | Apttus config fields and Rollup fields (apprx 7 fields are open to discuss with Digicert), rest other fields are in the RCA now. Auto population logic is in progress - Tharun needs to work on it. ETA - 08th DEC 08-DEC - Apttus config fields and Rollup fields (2 Roll up fields) (approx 7 fields are open to discuss with Digicert) - Alison doesn't have any idea and only Rakesh can help here, and he is in PTO. Rohit Shangle- X plan to discuss with Digicert on this to clarify. Auto population logic is in progress - Tharun needs to work on it. ETA - 08th DEC 09-Dec - Tharun needs to handover to Nagalakshmi the Auto population logic 10-Dec - Auto population logic: TDD is required. Suggestion: Via Context Definition - Need a discussion how to complete it 11-Dec - Bittu is working on the solution and need help from Nagalaksmi and Ramesh 12-Dec - Bittu will provide the list of fields where we are facing the problem and Nagalakshmi will help to solve. Fields provided by Bittu. Nagalakshmi needs to connect with Ramesh
Story | RCA-362 | BOM integration approach to be established based on RCA objects and fields | RCA-26 | Integration | Sprint-3 | Open | Pramod | TBD | Digicert, Neelima , Ramesh | Dependency : 1- RCA-1162 :Fields need to be created in the RCA object (Orders & Assets) Inbound & Outbound Fields need to be created. Pramod is in discussion with Ramesh for these fields. Note : Current focus on the Available fields only in RCA. 08-Dec - Neelima and Ramesh will discuss with Digicert today for the open questions 09-DEC - Solution Document needs to be updated by Pramod by 10th Dec 10-Dec - Agreed by Digicert on the above request. Need to share the MOM of the agreement with Digicert. Team is working on the Split of SOQL 11-Dec - Pramod needs to review the created fields for the Order and Order Line Items created till the time and planning to complete the SOQL. 12-Dec - Order Fields - In Source Apttus, over 200 fields, need to check in the RCA system how many fields are there is created. SOQL will be completed by 17th Dec'25
Story | RCA-277 | Migration approach from Apttus asset into RCA assets | RCA-25 | Data Migration | Sprint-3 | Open | Pramod | TBD | Vinutha & Sudha & Rohit & Neelima | 08-Dec - Dependencies : 1- Finalization on the Asset Line Item Fields are open from CPQ Team - Need team who can analyze the Fields (Srilekha is working on it) 2- Process for Cancellation of Assets , Superseading of Assets and Infulfilment of assets ( Dependency - First on Salesforce , 2nd Digicert) 3- Open for the Review and confirmation on the proicess flow 09-Dec - Solution Document needs to be updated by Pramod by 10th Dec 10-Dec - Source of Product Data file needs to be provided for the verification Solution Document needs to be updated by Pramod by 10th Dec 11-Dec - Source of Product Data file needs to be provided for the verification - Neelima , Rohit Solution Document in review with Vinutha and Sudha 12-Dec - Waiting for the update from Sudha and Vinutha on the solution
Story | RCA-274 | Migration approach for Apttus agreements into Contract object in RCA | RCA-25 | Data Migration | Sprint-3 | Open | Pramod | TBD | Vinutha & Raj & Karthik | 08-DEC 1- Process Flow needs to be reviewed with Vinutha and Raj 2- Solution Document needs to prepare 3- Need to re-discuss with Karthik on the process flow. 09-Dec - Discussion pending with Karthik , Solution Document needs to be updated by Pramod by 10th Dec 10-Dec - Solution Document needs to be updated by Pramod by 10th Dec 12-Dec - Solution needs to be updated by Pramod.
Story | RCA-275 | Migration approach for Apttus orders into RCA based on order fulfilment date (last 3-5 years) and dollar amount, order volume | RCA-25 | Data Migration | Sprint-3 | Open | Pramod | TBD | Vinutha & Raj & Rohit & Neelima Digicert Salesforce | 08-DEC 1- Process Flow needs to be reviewed with Vinutha and Raj 2- Solution Document needs to be ready by next week 3- Finalization on the Order and Order Line Item Fields - This will be going on and it will be added as when proceed. Order Cancellation Flow - Not Ready - Dependency on Digicert Superseding status flow - Not Ready - Dependency on Salesforce& Digicert Amed flow - Not Ready - Dependency on Salesforce & Digicert 09-Dec - Only Dependencies open Order Cancellation Flow - Not Ready - Dependency on Digicert Superseding status flow - Not Ready - Dependency on Salesforce& Digicert Amed flow - Not Ready - Dependency on Salesforce & Digicert Solution Document needs to be updated by Pramod by 10th Dec and review with Vinutha 11-DEC - Only Dependencies open Order Cancellation Flow - Not Ready - Dependency on Digicert Superseding status flow - Not Ready - Dependency on Salesforce& Digicert Amed flow - Not Ready - Dependency on Salesforce & Digicert Happy path is covered in the solution document and shared with Sudha and Vinutha for review. 12-Dec - No updates received on the Solution Review. Order Cancellation Flow - Partial cancellation of the orders asked by Sudha to check it.(Inprogress) Assets are not cancelled, only orders are cancelled. (same for parial and complete order)
Story | RCA-268 | Migration approach for inflight Apttus quotes into RCA based on pre-defined business criteria (Status, creation date etc.) | RCA-25 | Data Migration | Sprint-3 | Open | Pramod | TBD | Vinutha & Raj & Rohit & Neelima Digicert Salesforce | 08-DEC 1- Process Flow needs to be reviewed with Vinutha and Raj 2- Solution Document needs to be ready by next week 3- Bundle Products need to be created with a Charge Type - In Progress 4- Quote Header Status Mapping - Need confirmation from the CPQ Team whether the mappings are correct or not - Rohit will check with Pramod 5- Finalization on the In-flight Quotes Fields are open from CPQ Team - This will be going on and it will be added as when proceed. 10-Dec - Process Flow needs to be reviewed with Vinutha and Raj - Will review with Sudha Bundle Products need to be created with a Charge Type - In Progress Quote Header Status Mapping - Need confirmation from the CPQ Team whether the mappings are correct or not - Rohit will check with Pramod 11-Dec - Solution document is in review with Sudha & Vinutha Bundle Products need to be created with a Charge Type - In Progress Quote Header Status Mapping - In discussion with Rohit Dependency on Digicert : Whether team can leverage the exisiting order forms in case of generated , presented and accepted proposals.
Story | RCA-205 | Enable contract amendments | RCA-28 | CLM | Sprint-3 | Open | Karthik V | 2025-12-16 | Karthik V | 09-Dec - Need clarification 10-Dec - Need to discuss with Karthik V 11-Dec - Karthik V needs to provide the solution and walkthrough should be done with the DEV Team
Story | RCA-202 | Desired analytics from CLM system (e.g. clause negotiation frequency, approval process timelines, legal rep turnaround times by agreement type) | RCA-28 | CLM | Sprint-3 | Open | Srinivas T, Karthik | 2025-12-19
Story | RCA-185 | Setup standard reports and Dashboards including the cycle time reports on the Agreement | RCA-28 | CLM | Sprint-3 | Open | Karthik | 2025-12-17
Story | RCA-195 | Termination: Ability to notify the users (Requestor, Agreement Owner, Channel Manager) when an Agreement is terminated. Use the Out of the box email template and content. | RCA-28 | CLM | Sprint-3 | Open | Karthik | 2025-12-18
Story | RCA-189 | Cancellation: Ability to notify the users (Requestor, Agreement Owner) when an Agreement is canceled. Use the Out of the box email template and content | RCA-28 | CLM | Sprint-3 | Open | Karthik | 2025-12-18
Story | RCA-190 | As part of the Amendment, the system copies the details of the activated Agreement record into the Amendment record. A relationship is established in order to maintain the co-relation between the two records. | RCA-28 | CLM | Sprint-3 | Open | Srinivas T | 2025-12-18
Story | RCA-187 | Agreement execution actions: Amend, Renew, Expire and Terminate buttons should be available post Agreement Activation. | RCA-28 | CLM | Sprint-3 | Open | Mahalakshmi | 2025-12-17
Story | RCA-188 | Ability to re-submit for e-signatures in case of any Signatures declined during the signature process. | RCA-28 | CLM | Sprint-3 | Open | Srinivas T | 2025-12-18
Story | RCA-181 | Auto populate Terms & clauses from MSA onto the account and the quote | RCA-28 | CLM | Sprint-3 | Open | Mahalakshmi | 2025-12-17
Story | RCA-182 | Once the Agreement is Generated and signed, there should be no change in the products/pricing | RCA-28 | CLM | Sprint-3 | Open | Mahalakshmi | 2025-12-18
Story | RCA-179 | Once the contract is created and signed, it should be auto -attached to the quote. | RCA-28 | CLM | Sprint-3 | InBuild | Mahalakshmi | 2025-12-17
Story | RCA-180 | Sales Rep should should have the ability to download the contract document and send it to customer of offline review | RCA-28 | CLM | Sprint-3 | Build completed | Lakshmi Narayana | 2025-12-17
Story | RCA-171 | System should auto populate the clauses in the contract document based on the contract type | RCA-28 | CLM | Sprint-3 | Open | Lakshmi Narayana | 2025-12-17 | Karthik V | 15-Dec - AC need for this user story
Story | RCA-170 | Eliminate manual validations on the contract dates and MSA status on the agreements | RCA-28 | CLM | Sprint-3 | Open | Lakshmi Narayana | 2025-12-18
Story | RCA-130 | Create a flag on the renewal quote to indicate that some changes made in the clause so it'll save time for reps on the renewals to skip the some of the approvals | RCA-28 | CLM | Sprint-3 | Open | Srinivas T | 2025-12-18
Story | RCA-51 | To Enable Delegate Approvlas - Allow approvers to Delegate the pending approvals to the members from the approval queue | RCA-29 | Approval Management | Sprint-3 | On Hold | Vinutha & Neelima | TBD | Salesforce | Clarification needed from Salesforce
Story | RCA-69 | Enable smart approvals in RCA | RCA-29 | Approval Management | Sprint-3 | On Hold | Mahitha & Gaurav | TBD | Salesforce | RCA-69 and RCA-65 having same solution OOTB Smart Approvals is not working. 05-Dec - Salesforce Case is raised by Mahitha #472143757
Story | RCA-60 | Custom actions on approval notifications | RCA-29 | Approval Management | Sprint-3 | Open | Nagalakshmi & Prasanth | 12/09/2025 12/10/2025 12/12/2025 12/15/2025 | Nagalakshmi | 25-Nov : Completed the build and unit testing in the Sprint-1. Need to update JIRA with the results and Conflguration log. 26-Nov - AC and Solution need to discuss 28-Oct - Difference identified in the SDD and AC. Need to discuss with Neelima for the update required in the solution document. 02-Dec - Build in progress and on track now for the closure. 05-Dec - Build will be completed by next week Tuesday 09-Dec - Part of Nagalakshmi is open to close in the Build 10-Dec - Open from Nagalakshmi and she is on sick leave today 11-Dec - Prasanth will complete by tomorrow 15-Dec - Build completed. Need to check with Nagalakshmi
Story | RCA-57 | Enable email based approvals in Salesforce RCA | RCA-29 | Approval Management | Sprint-3 | Open | Nagalakshmi & Prasanth | 12/09/2025 12/10/2025 12/12/2025 12/15/2025 | Nagalakshmi | Same as RCA-60 15-Dec - Build completed. Need to check with Nagalakshmi
Story | RCA-186 | Ability to notify the team on every stage/status changes on the Agreement life cycle | RCA-28 | CLM | Sprint-3 | Open | Lakshmi Narayana | TBD | Digicert (Lindsey) | Dependency : 1- After the demo we will have the clarity on Solution Stages and Email Templates
Story | RCA-784 | As a Sales user I should be able to select the Inflation Adjustment language to appear on the Super Order Form | RCA-34 | Quote Management | Sprint-3 | Open | Karthik A | TBD | Digicert (Lindsey) | Language is missing and needs to be discussed with Legal
Story | RCA-506 | As a Sales/BD user I should be able to check/uncheck "Marketing Summary" field before generating proposal document (OF) on the quote. | RCA-28 | CLM | Sprint-3 | Open | Mahalakshmi/ Karthik V | 11/27/2025 12/03/2025 12/05/2025 TBD | Digicert (Lindsey) | 1-Dec - Pending (Docusign Signature) - Need to discuss with Karthik V 2- Dec - Unit Testing in progress 08-DEC - Marketing Summary Details are not provided by Digicert. 09-DEC - Karthik will discuss with Lindsey today to get the details.
Story | RCA-200 | Reps should be able to copy the link of the document to send it to customer for review | RCA-28 | CLM | Sprint-3 | In Unit Testing | Srinivas T | 2025-12-05 |  | Dependency: Need the Solution document We are checking on the review process and we have raised a case with Salesforce. Case No: 472145203 05-Dec - We will have the call with Salesforce today 08-Dec - Requested call with Salesforce. Awaiting Response. 11-Dec- Salesforce dependency is closed and team is doing unit testing
Story | RCA-201 | Business desk should be able to customize the email notification subject and template of the document that’s being sent to the customer for review. | RCA-28 | CLM | Sprint-3 | In Unit Testing | Srinivas T | 2025-12-05 |  | Dependency: Need the Solution document We are checking on the review process and we have raised a case with Salesforce. Case No: 472145203 05-Dec - We will have the call with Salesforce today 11-Dec- Salesforce dependency is closed and team is doing unit testing
Story | RCA-198 | Sales Rep should have the ability to pull customer email addresses to select and send the document to customer for redlining | RCA-28 | CLM | Sprint-3 | In Unit Testing | Srinivas T | 2025-12-05 |  | Dependency: Need the Solution document We are checking on the review process and we have raised a case with Salesforce. Case No: 472145203 05-Dec - We will have the call with Salesforce today 11-Dec- Salesforce dependency is closed and team is doing unit testing
Story | RCA-203 | Self-Service agreement activation process | RCA-28 | CLM | Sprint-3 | In Unit Testing | Srinivas T | 2025-12-05 |  | We are checking on the review process and we have raised a case with Salesforce. Case No: 472145203 11-Dec- Salesforce dependency is closed and team is doing unit testing
Story | RCA-191 | Ability for the users to redline and track the changes made to the system generated document. | RCA-28 | CLM | Sprint-3 | In Unit Testing | Srinivas T | 2025-12-05 |  | Need 365 access for redlining For365, Digicert has set up a call for 12/02 and it is still not working. The team has set up a call on 12/03 to restart the who process from scratch 04-DEC - Dependencies resolved We are checking on the review process and we have raised a case with Salesforce. Case No: 472145203 11-Dec- Salesforce dependency is closed and team is doing unit testing
Story | RCA-264 | Renewal opportunity auto-creation : From New Logo, and renewals | RCA-30 | Opportunity Management | Sprint-3 | Build completed | Mahitha | 2025-12-09 | Salesforce | 26-Nov - POC in the DEMO org in progress, and the ETA needs to be confirmed by EOD. 27-Nov - ETA- 27th Nov for the POC 02-Dec - Some modifications are required to complete the build. Mahitha needs to look into it. #472153980 08-Dec - Team is looking into the solution and can be confirmed asap. Opportunity is getting created, Solving errors those are getting triggered because of existing old flows/automations to create Opportunity Products
Story | RCA-305 | Ability to have multiple price adjustments e.g. % discount, absolute discount, price override, Uplift, etc. | RCA-36 | Pricing Management | Sprint-3 | Open | Mahitha | 12/10/2025 12/12/2025 |  | 1-Dec - POC is in progress and will reach out to Pankaj on 2nd Dec if required. #472113638 - Adjustment type - Discount Percentage is automatically setting to 0 04-Dec - Custom solution needs to be approved by Neelima 08-Dec - Neelima will check today and confirm. 09-Dec - Discussion is open with Salesforce on the case #472113638 12-Dec - Case is resolved. Deactivate the validation and do the unit testing and then activate.
Story | RCA-269 | Maintain audit fields in RCA on migrated objects and data based on created by/modified by user and dates | RCA-25 | Data Migration | Sprint-3 | Open | Pramod | 2025-12-16 | Ramesh | Need clarification on the Solution. 09-Dec - Need to discuss with Vinutha 11-Dec - AC and SDD are updated and build is progress. Need to create some fields which needs to discuss with Ramesh
Story | RCA-53 | Implement Auto-escalations for quote approvals | RCA-29 | Approval Management | Sprint-3 | Unit Testing in progress | Jyothi | 12/13/2025 12/15/2025 |  | 11-Dec - build completed,need to show to nagalakshmi. 11-Dec : The template will be attached by Rohit 12-Dec - Will be closed by 13th Dec 15-Dec - Config log needs to update in JIRA
Story | RCA-66 | Ability to trigger Approval email notifications to respective users | RCA-29 | Approval Management | Sprint-3 | Unit Testing in progress | Harchanran | 2025-12-12 |  | 15-Dec - Config log needs to update in JIRA